SAICH PLATFORM

(Southern African Intangible Cultural Heritage Cooperation Platform)

UNESCO/FLANDERS PROJECT ON STRENGTHENING SUB-REGIONAL COOPERATION AND NATIONAL CAPACITIES IN SEVEN SOUTHERN AFRICAN COUNTRIES FOR IMPLEMENTING THE 2003 CONVENTION FOR THE SAFEGUARDING OF INTANGIBLE CULTURAL HERITAGE (2018)

First Progress Report

Part I

NARRATIVE REPORT ON THE INCEPTION PHASE:

First Coordination Workshop and Follow-up Activities

15 March 2019

Southern African ICH Cooperation Platform Meeting

(SAICH Platform)

UNESCO/FLANDERS PROJECT ON STRENGTHENING SUB-REGIONAL COOPERATION AND NATIONAL CAPACITIES IN SEVEN SOUTHERN AFRICAN COUNTRIES FOR IMPLEMENTING THE 2003 CONVENTION FOR THE SAFEGUARDING OF INTANGIBLE CULTURAL HERITAGE

Lilongwe Hotel, 11-12 February, 2019

Final Draft Report

15 March 2019

Table of Contents

Abbreviations………………………………………………………………………………….4

Preamble and Workshop Objectives………………………………………………………......5

DAY 1 MONDAY 11 FEBRUARY 2019…………………………………............................6

Official Opening Ceremony………………………………………………………………...6

Remarks by Representative of the UNESCO Regional Office for Southern Africa………..6

Remarks by the Principal Secretary for Civic Education, Culture and Community Service 7

Review and Adoption of the Workshop Program…………………………………………..8

General Review of Activities carried out during 2016-17 vis-à-vis Expected Results and Outputs of the New Project Phase…………………………………………………………..8

Strengthening the Existing Program and Reinforcing the SAICH Cooperation Platform….9

Standardising the Structure, Guidelines and Operational Procedure of the National ICH Committees…………………………………………………………………………….….10

Further Development of and Support for the Personnel and Structures for Implementing the ICH Convention in the Communities and at the National Level………………………….10

DAY 2 TUESDAY 12 FEBRUARY 2019………………………………………………….11

Domesticating the 2003 ICH Convention by Translating it into Selected Languages that are Widely Spoken in the Seven Participating Countries…………………………………….11

Enhanced Platform Website and ICH Database – setting up, training, maintenance, access and use……………………………………………………………………………………..11

Advice on Compiling Nomination Files and International Assistance Requests………….12

Special Note……………………………………………………………………………….12 SAICHA Net………………………………………………………………………………13

Looking at the Future – action plans and sustainability……………………………………...13

Action Points Table...…………………………………………………………..………..…...14 Suatainability Strategy…………………………………………………………………….....15 Addendum…………………………………………………………………………………...15 CLOSURE……………………………………………………………………………..….....16

ANNEXURES………………………………………………………………………………17

Annex 1: Major Activities and Deliverables of the New Phase of the Project.....…………...17

Annex 2: Lilongwe Workshop Program …………………………………………………….19 Annex 3: List of Workshop Participants………………………………………….................21 Annex 4: Contract Guidelines for Translation of the ICH Convention……………………..23 Annex 5: SAICH Platform Database Access Policy………………………………………...24 Annex 6: Proposal to set up SAICHA-Net………………………………………………….26

Abbreviations

CUT		-	Chinhoyi University of Technology

FPP		-	Focal Point Person

IAR		-	International Assistance Request

ICH		-	Intangible Cultural Heritage

IGC		-	Intergovernmental Committee

NATCOM	-	National Commission for UNESCO

NICHC	-	National Intangible Cultural Heritage Committee

ODs		-	Operational Directives (of the Convention)

ROSA		-	Regional Office for Southern Africa (UNESCO)

RL		-	Representative List (ICH elements)

SADC		-	Southern African Development Community

SAFE		-	Safeguarding Plans (for ICH)

SAICH Platform -	Southern African Intangible Cultural Heritage Cooperation Platform

SAICHA-Net	-	Southern African Intangible Cultural Heritage Academic Network

Preamble and Workshop Objectives

[Verbatim as previously circulated by the SAICH Platform Coordinator, Professor Herbert Chimhundu]

The purpose of the workshop is to formally kick-start activities of the final phase of this capacity building project on ICH safeguarding in seven countries in Southern Africa, which is supported by the Flanders Government under the auspices of the UNESCO Regional Office for Southern Africa (ROSA). This sub-regional cooperation project is coordinated by the SAICH Platform, which was created for that purpose in 2015 and is hosted by Chinhoyi University of Technology (CUT) in Zimbabwe.

The five major activities of this new phase of the project are:

- Upgrading and constant maintenance of the SAICH website and database to build a strong tech hub that will provide a vibrant and interactive platform for ICH information dissemination, sharing and dialoguing;

- Domesticating the 2003 ICH Convention by translating it into selected languages that are widely spoken in the seven participating countries;

- Producing and disseminating awareness-raising materials, both in print and in audio-visual formats;

- Training (ToT) in elaboration of safeguarding plans (SAFE) while also addressing issues of gender equality and ethics; and

- Analysing the context and challenges as well as revitalizing the National Intangible Cultural Heritage Committees of the participating countries

The new project phase will be very intensive and it will only run until June 2019. During this short period, three workshops will be held, starting with the workshop in Malawi in February to plan these activities in detail, followed by a SAFE training workshop in Lesotho in April1, and winding up with a review workshop in June most probably on a virtual platform2.

Thus the planning workshop in Malawi will ensure that the final stage of the chain of phases of ICH safeguarding and capacity building in Southern Africa will guide and assist the structures that have already been established in previous phases of this project since its inception in 2010, i.e. national ICH committees, ICH database, the Platform and the proposed network of academic institutions in their strategic planning towards self-sustainable functioning3.

- Moved to May to allow more time for translations of the 2003 ICH Convention and other activities as per Action Points Table that is given at the end of this report.

- Purchase and installation of a video conferencing kit is being processed and will be completed before the second workshop in Lesotho, which will have a large training component.

- Teleconferencing equipment has been prioritized because it will not only reduce the need for physical meet-ups (roundtable meetings) but it will also boost capacity for continuity of sub-regional cooperation to assure sustainability beyond the life of the current UNESCO/Flanders project.

# WORKSHOP PROCEEDINGS

# DAY 1 MONDAY 11 FEBRUARY, 2019

## Official Opening Ceremony

Mr. C.J. Magomelo, the Program Officer for Culture for Malawi National Commission for UNESCO, was the Director of Ceremonies. He gave welcome remarks to all delegates and facilitated the introductions session. The first speaker was the Acting Executive Secretary of the Malawi National Commission for UNESCO, Mr.  D. Mulera, who gave an overview of UNESCO programmes and the projects which the country has been involved in.

Then Professor H. Chimhundu, the SAICH Platform Coordinator at Chinhoyi University Technology (CUT), acknowledged and thanked the Government of Malawi through the guest of honour for hosting the meeting with the support of Regional Office in Southern Africa (ROSA). He highlighted that CUT provided technical and secretariat support for the SAICH Platform. He thanked all those who had been involved in the preparations for the workshop in Malawi, and all the country focal persons who had worked within the Platform consistently from 2015. Prof. Chimhundu explained how the project operated at CUT, observing that the SAICH Platform office was not manned by any full-time staff. However, efforts were now underway to get some staff to be seconded to the Platform from other units of the university to work there on a full-time base.

The Coordinator also highlighted that, after the winding-up in 2017 of the previous phase of the project “Strengthening sub-regional cooperation and national capacities in seven Southern African countries for implementing the 2003 Convention for the Safeguarding of Intangible Cultural Heritage”, more funding had been received from the Flanders government through UNESCO for a new phase in 2018-19. No doubt the donor had been impressed with the outputs from the previous phases. The new grant was for a 6- month project extension, with two major objectives being to enhance the technology hub and to work towards sustainability.

Remarks by Representative of the UNESCO Regional Office for Southern Africa (Mr. R. Bunhiko)

Mr R. Bunhiko expressed gratitude to the Government of Malawi, the Malawi National Commission for UNESCO and the SAICH Platform coordinators for hosting the meeting and for all the facilities and logistics which undoubtedly highly contributed to the success of the workshop.

He explained that the umbrella project (“Strengthening sub-regional cooperation and national capacities in seven Southern African countries for implementing the 2003 Convention for the Safeguarding of Intangible Cultural Heritage”) was designed within the framework of UNESCO’s global capacity-building strategy which was established in 2009 to address the challenges of effectively implementing the provisions of the 2003 ICH Convention and its Operational Directives (ODs). This global strategy was meant to assist States Parties to master the concepts, measures and mechanisms proposed by the normative instrument for safeguarding intangible cultural heritage. The States Parties to the 2003 Convention had since shown interest in this strategy and donors had provided generous support for its implementation through the Intangible Cultural Heritage Fund and Funds-in-Trust. Through this support, a set of projects and curriculum materials were developed and a network of experts had been trained to use these materials in delivering training and providing advisory services to States Parties. So far about 70 countries have benefited from the global strategy in enhancing their capacities for safeguarding living heritage, Malawi included and with Mr Lovemore Mazibuko being one of the most recognized experts.

This project was designed as the third (3rd) and final stage in the efforts to strengthen sub-regional cooperation and national capacities in Southern African countries in the implementation of the 2003 Convention for the Safeguarding of Intangible Cultural Heritage. This third phase had been designed to guide and assist the successfully established Platform structures in their strategic planning and to progress towards self-sustainable functioning. As such the SAICH Platform and its auxiliary components in the form of the ICH Inventorying Management System (IMS) and the National ICH Committees (NICHCs) of the 7 participating countries would be guided accordingly. The countries in this grouping were Botswana, Eswatini, Swaziland, Lesotho, Malawi, Namibia, Zambia and Zimbabwe.

Therefore, the principal objective of this last project phase therefore was to strengthen the SAICH Cooperation Platform so that it can effectively support the continuity of intangible cultural heritage safeguarding processes in the seven participating States Parties of Southern Africa. It was expected that strengthening of the SAICH Platform mechanism of cooperation would further improve the efficiency of implementing the 2003 ICH Convention across the sub-region and would result in increased sustainability of the process at both country and sub-regional levels. In its implementation process, the project therefore was designed to enhance the capacity of the Information Management System (IMS) that had been previously developed by the platform, initially as a database of ICH elements that were inventoried in the communities and uploaded by Focal Point Persons in the participating countries. Enhancement of the IMS included building online resources to support new regional academic and technical training programmes in ICH that were being developed as a result of the project growing and evolving. This, he believed, was expected to stimulate the establishment of more collaborative sub-regional networks and partnerships for information sharing and exchanges on ICH and related areas. Long-term impacts of this phase of the project on local communities would be assured by engaging NICHCs and building capacities on safeguarding plans, community based inventorying and digital content production, expanding collaborative networks and partnerships for information sharing and exchanges on ICH, as well as domesticating the 2003 ICH Convention by translating it into local languages

Remarks by the Principal Secretary for Civic Education, Culture and Community Service (Mrs. I. Luhanga)

The Principal Secretary was delighted to witness and officially open the launch of the final phase of the capacity-building project on the safeguarding of intangible cultural heritage in seven countries in Southern Africa, which were participated in this project with support from the Flanders Government under the auspices of UNESCO. Mrs Luhanga was pleased to note that Malawi had ratified the 2003 Convention for the safeguarding of ICH (also known as the living heritage) in March 2010. Since then Malawi had implemented a number of projects and programmes at national level that are aimed at safeguarding this heritage. These projects included three publications on the living heritage that were collected from different parts of the country and were regularly updated by a team of experts comprising members of the National Intangible Cultural Heritage Committee of Malawi, the Department of Museums and Monuments, and the Malawi National Commission for UNESCO. She stressed that the implementation of the convention of safeguarding the ICH was first and foremost the responsibility of the communities who were the owners of the heritage, and that governments only facilitated the processes to ensure that there were favourable conditions for the communities to play their rightful roles. She emphasised the importance of was made for creating a database for the inventoried ICH elements and ensuring access to these elements by the public through various platforms. She also encouraged the participants to brainstorm on how of making te implementation of the Convention could be made to contribute to national development through cultural industries and employment creation. In conclusion, Mrs Luhanga expressed sincere gratitude to the Flanders government, to UNESCO, the SAICH Platform Coordinators and the Malawi National Commission for UNESCO for successfully organising the current workshop and she appealed to all delegates to draw benefits for their respective countries.

Session 2: Chair - Mr. L. Mazibuko (Focal Point Person – Malawi)

## Review and adoption of the workshop program

The program was interrogated and it was agreed that it be adopted on the understanding that, during the presentations and discussions, special attention would be paid to how communities could benefit from the implementation of the ICH Convention, and how far countries had gone with policy development, especially the inclusion or mainstreaming of ICH issues. Deliberations were also expected to highlight the inclusion of the youths and gender participation in line with the Convention.

General review of activities carried out during 2016-17 vis-à-vis expected results and outputs of the new project phase (Mr. R. Bunhiko – ROSA Representative)

The project being implemented by UNESCO ROSA in partnership with the SAICH Platform Coordinators had been funded by the Flanders Government since 2013. The SAICH Platform was created towards the end of the first phase 2014-15. During the second form 2016-17, inventorying activities had been carried out in the participating countries and a total 97 elements were uploaded onto the SAICH Database. The 3rd and final phase of the project was now intended to strengthen of existing structures of information management and dissemination. The project duration was from January to June 2019. ROSA had been emphasising the need for sustainability of the sub-regional cooperation mechanism so as to sustainably support national efforts in safeguarding the intangible cultural heritage of communities in Southern Africa beyond Flanders-funded project. This had seen some policy, legal and institutional frameworks being established or improved at the national level, in order to provide a national environment suitable for safeguarding of intangible cultural heritage. There had been also strengthening of human resources at the national level (through FPPs) to facilitate the implementation of the 2003 Convention with the broadest participation of the communities.

The principal objective of this last project phase was, therefore, the strengthening of the sub-regional cooperation platform mechanisms so that they could effectively support sustainable and continuous ICH safeguarding processes in the participating States Parties to guide the structures that were already designed for the same. There would be a detailed assessment of the SAICH IMS and the communication contexts of the web interface particularly from the point of view of their sustainability and the context and challenges of the National Intangible Cultural Heritage Committees (NICHCs) of the seven participating countries (safeguarding work plans). Successful research aspects of the SAICH Platform functioning needed to be done in the fields of ICH policies, ICH ethics, and the role and potential of ICH in tertiary education (e.g. esp. activating the ICH Research Group at CUT and the SAICHA Network). There will be continued work on the SAICH database and development of better nomination dossiers with the hope of increase in the number of successful International Assistance Requests and the growth of the Platform.

## Strengthening the existing program and reinforcing the SAICH Cooperation Platform

The Platform was created in February 2015 to function as the Secretariat for the project; to coordinate activities in the participating countries and to provide a forum for discussion and exchange of information on ICH safeguarding. As hosts of the SAICH Secretariat, CUT allocated office space from where SAICH Coordinators operate. The expectation was that, as cooperation and national capacities in the sub-region were further strengthened for implementing the 2003 Convention, the Platform itself would grow into a vibrant research, documentation, resource and training centre for ICH, and also as a facility for consultancy and advisory services for the arts and culture sector within the sub-region and beyond. CUT had committed to these initiatives by providing the host arrangements, technical support and assistance with project administration, accounting and reporting. The choice of a university that has a technology bias was deliberate as the SAICH Platform needed to build and maintain virtual networks. Furthermore, the university had an active group of academics with research interests in ICH-related disciplines and it was now also taking a lead in establishing the SAICHA-Net, a network of ICH scholars in the region.

Since the current phase of the project was going to be the final one, stock had to be taken of achievements and outcomes of the project. Therefore, the current workshop would have to answer the following questions; do we still need the platform to continue; if yes, how then can the platform be strengthened and reinforced and how can its sustainability be guaranteed?

## Standardising the structure, guidelines and operational procedure of the National ICH Committees

A NICHC is a collection of individuals who bring unique knowledge and skills which augment the knowledge and skills of a formal organization for the effective implementation of ICH programs. It does not have formal authority to govern the organization, rather it serves to make recommendations and/or provide key information and materials to the Ministry for Culture. A properly composed and structured NICHC can be a tremendous complement to the effectiveness of the Ministry responsible for culture.

For any NICHC to be effective, it has to meet some criteria. Its composition should comprise a sufficient range of expertise to accomplish the organization’s mission; its terms of reference should be written; its roles and responsibilities must be clearly described; and its means of communication must be inclusive and formal.

Further development of and support for the personnel and structures for implementing the ICH Convention in the communities and at the national level (Mr. E. Kautondokwa – FPP Namibia)

Prof. Jacob Mapara and Mr. Erastus Kautondokwa were the presenters for session 3 with Ms Tokelo  Mapena (FPP Lesotho) chairing. The first section of this session looked at further development of, and support for, the personnel and structures for implementing the ICH Convention in the communities and at the national level. Mr. Erastus Kautondokwa shared the Namibian experience in developing and supporting community members and government officials in the implementation of the 2003 ICH Convention. He stated that for the period 2010 to 2015, members of various communities as well as regional officials in Namibia were trained as Trainers-of-Trainers on ICH awareness raising, community based inventorying and documentation. The aim was to enhance the sustainability of capacity building at the community level in Namibia’s fourteen administrative regions. The observation made was that further assistance was required by SAICH member states to enable government officials as well as trained community members to be able to complete nomination forms of elements inventoried and documented in their respective localities by themselves. Further training on requesting international assistance to both officials and trained community representatives was still needed. These additional capacity building activities would empower community members to plan and implement projects at the community level.

# Day 2 TUESDAY 12 February 2019

Domesticating the 2003 ICH Convention by translating it into selected languages that are widely spoken in the seven participating countries (Prof. J. Mapara – Associate Coordinator: SAICH Platform)

In the second section of session 3 on the domestication of the 2003 ICH convention, Prof. Jacob Mapara, the Associate coordinator of the SAICH platform at CUT, pointed out the various ways in which the 2003 convention on ICH could be domesticated. These included translating it into local languages, and aligning it with or and including it in countries’ laws. He advised country FPPs to choose widely spoken languages and to use simple and gender sensitive language when translating the convention in their respective countries. Drawing from his experience as an executive member of National Constitution Translation Committee (NCTC) of Zimbabwe, Prof. Mapara hilighted some of the procedures that should be considered during the translation assignment. He emphasised the need for setting up a translation committee which, among other duties, would identify accredited agencies or individuals capable of providing a professional and quality translation service. He highlighted some of the benefits that would come with the proposed translation of the ICH Convention and related documents such as creating a sense of ownership for both the concerned state parties and the speakers of the languages of targeted communities.

During the ensuing discussion on this topic, Prof. Chimhundu informed the meeting that each of the seven countries would be allocated a budget allocation of U$2000.00 for the translation of the convention exercise. He emphasised that for this project, only the text of the Convention and not all the complete basic texts should to be translated by May 2019, i.e. excluding the Operational Directives (ODs).

## Enhanced Platform website and ICH database, setting up training, maintenance, access and use

On the second day of the coordination workshop, session 4 and 5 was chaired by Ms. Temahlubi Dudu Kambule Eswatini (Swaziland)’s Focal Point Person, while Mr. Eugene Ncube from CUT SAICH Coordinating Team made a presentation on enhancing the tech hub. Mr. Ncube outlined the primary objective of the IT consultants for the remaining period of the project as that of upgrading the website by providing links to the ICH Convention in English and other translated versions from the current project. He informed participants that the SAICH database currently had 97 ICH elements from the 7 member states with elements ranging from 1 to 47 per country. A major concern was raised that one or two member countries seemed hesitant to upload their ICH elements on SAICH database. FPPs were encouraged to continue uploading ICH elements onto the database. FPPs on the other hand, indicated that sometimes they faced challenges and could not get immediate technical assistance. It was also pointed out that there was no delete function that would enable them to delete trial information deposited on the site earlier.  Mr. Ncube assured SAICH users this would be rectified. Another concern raised vis-à-vis the use and access to uploaded ICH information was the lack of guidelines and policy on the operations of the site, for instance, the rights and regulations on the use of database materials.  Mr. Christopher Magomelo and Dr. Chanunkha volunteered to draft and share policy guidelines before the next SAICH next coordination meeting in May 2019.

Mr. Nchube concluded his presentation with some slides showing video conferencing equipment that the SAICH Platform Coordinators were proposing to purchase and install to link up all the FPPs with the Tech Hub at CUT, as well as an illustration of production and dissemination of audio-visual publicity materials that could be produced by Platform members of the Platform.

## Advice on compiling nomination files and International Assistance Requests

During the 5th session, Mr. Munukayumbwa Munyima, the FPP for Zambia who was also a member of the Intergovernmental Committee (IGC) on ICH, made two presentations. In his first presentation on compiling files and International Assistance Requests (IARs), Mr. Munyima explained the purpose and types of international assistance that could be requested, as well as the process of decision process by the IGC.  He further elaborated on critical points regarding requests for IA such as the need for community involvement in the preparation of the requests and clear indication on roles that they and other stakeholders would play in the implementation of the projects or activities for which financial assistance was sought. He cautioned participants not to duplicate texts from other and or previously published material without proper acknowledgement. He urged SAICH member states to collaborate and request for financial assistance for multinational nominations of sub-regional and regional nature as they are of priority to the Bureau and the IGC.

In his second presentation on preparing nomination files, Mr. Munyima placed emphasis on the significance of factors such as community involvement in the identification of a need to nominate ICH elements to either of the two lists of ICH elements (the Representative List and the Endangered List) and to the register of Best Practices. He urged member states to ensure that nominations showed evidence of free and informed consent obtained prior to nomination. He pointed out that this was one of the grounds on which the multinational nomination of the mbira/sansi by Malawi and Zimbabwe could not be inscribed on the representative list of ICH during 13 COM. He however, thanked the two countries concerned for accepting the decision and agreeing to go back to rectify and resubmit.

Special Note

Country reports that were scheduled for session 6 on day 3 were not presented or discussed as these had been covered by the report for the previous phase of the project which ended in 2017. That report had been circulated again to the FPPs as background for the current meeting. Similarly, the two special reports on policy development on ICH in Southern Africa by Mr. Munyima and on the multinational nomination of the mbira/sansi for the Representative List by Mr. Mazibuko and Dr. Samwanda were not discussed for the same reason, although a brief update was given on the latter.

SAICHA Net – Prof. J. Mapara/C. Magomelo

To broaden the activities of SAICH Platform through extension networking activity for academics and heritage practitioners, a proposal was being made to involve tertiary education institutions in ICH safeguarding work. Prof. Jacob Mapara made a presentation on a concrete proposal that had been made to create a professional association called the Southern Africa Intangible Cultural Heritage Academic Network (SAICHA-Net). Prof. Mapara himself was one of the proponents of the network who had been assigned to draft the foundation document for SAICHA-Net at a sub-regional workshop that was attended mostly by academics in Harare on 28-29 August 2018. According to this document, which was now being shared with SAICH FPPs (see Annex 7), SAICHA-NET was being proposed to be set up as a network of tertiary institutions and academics that would operate under the auspices of the SAICH Platform. Its members would include relevant government ministries/agencies, academic institutions, groups or individuals interested in activities related to the preservation, protection and promotion of ICH through research, training and community engagement. The network’s objectives include fostering the development of the African epistemology such as the philosophy of Ubuntu/Botho/Unhu… (African Humanism).

# Looking at the Future – Action Plans and Sustainability

Since the current project is ending in June 2019, the meeting saw it necessary to come up with a comprehensive action plan to ensure outcomes that would lead to enhanced capacity, continuity of cooperation among the participating countries and sustainability of ICH safeguarding programs and activities after the life of the UNESCO/Flanders project. A set of deliverables was agreed upon, the activities to be carried out under each deliverable were described, lead persons and entities to take the responsibility for execution of specific tasks were identified and deadlines were set through to June 2019. All these are elaborated in the table below.

A strategy for sustainability was also developed. Its main feature is institutionalization of the SAICH Platform through creation of a UNESCO ICH Centre Category 2. The other components that would be incorporated in the process would be setting up of the proposed SAICHA-Net, stakeholder mapping, preparing and submitting a position paper to SADC, compiling and submitting more multinational nomination files, and vigorous resource mobilisation. The sustainability strategy is also elaborated in a separate table below.

Action Points Table from Coordination Meeting held in Malawi

|  | Deliverables | Description/ Activities | Responsible person/institution | Deadline |
| --- | --- | --- | --- | --- |
|  | Coordination workshop 1 Malawi | Inception and planning (Meeting) | Malawi NATCOM, | 12/02/19 |
|  |  | Report submission | SAICH Coordinators | 28/02/19 |
|  | Enhanced SAICH Platform website and ICH database | Upgrading | CUT SAICH | 31/02/19 |
|  |  | Training of technical personnel at CUT |  | April 2019 |
|  |  | maintenance of the database |  | Ongoing |
|  |  | Develop Policy for access and use (guidelines on e.g. rights and regulation on the use of database materials) | FPPs, Mr Magomelo and Dr. Chanunkha | 31 March 2019 |
|  | Guidelines on structure and TORs of NICH Committees or equivalent national agencies [FPPs] | Development of the guidelines (with inputs from FPPs) | Mr. Mazibuko and FPPs | 31 March 2019 |
|  | Coordination workshop 2 - Lesotho | Training FPPs (Lesotho) on upgraded database and website | CUT SAICH | April 2019 |
|  |  | Validation of SAICH ICH related Policies and guidelines | Mr Mazibuko, Mr Magomelo and Dr Chanunkha |  |
|  | Translation of the 2003 Convention into selected languages | - Contract details communicated - Establishment of the translation committees. - Engagement of translators - Translated text of the 2003 ICH Convention in at least one language per country (draft) | Prof Mapara, FPPs | 28/02/19 31/03/19 |
|  | Awareness-raising materials produced | Compilation of reports, documents, newsflashes, newsletters, articles etc. | FPPs, Mr. Ncube (Tech) | Ongoing |
|  | Training (ToT) in elaboration of safeguarding plans (SAFE) | Training Session during workshop 2 | CUT SAICH | April 2019 |
|  | Research publications on ICH safeguarding and ethics, gender equality and youth | Commissioning of a researcher | CUT SAICH | (virtual) June 2019 |
|  | Coordination workshop 3 (virtual) | Review, reporting and closure | CUT tech | June 2019 |

Sustainability Strategy

|  | Deliverables | Description/ Activities | Responsible person/institution | Deadline |
| --- | --- | --- | --- | --- |
|  | Category 2 Centre | Guidelines communicated by ROSA | CUT SAICH | 22/02/19 |
|  |  | Draft Proposal | CUT SAICH | April 2019 |
|  |  | Review | FPPs | 2nd Workshop) April 2019 |
|  | SAICHA-NET | Review of draft constitution | Mr Magomelo and Prof Mapara | 2nd workshop) April 2019 |
|  | Stake holder mapping | identifying potential stakeholders and partners | FPPs | June 2019 |
|  | Position Paper to SADC | position paper to SADC submitted through ROSA | Ms Kubanji, Dr Samwanda, and Mr Munyima |  |
|  | Multinational Nomination files | development of multinational nomination file (7 Days Brew) | Mr Mazibuko | April 2019 |
|  | Resource Mobilization strategy | - engage resource mobilization expert - International assistance requests - Participation Programmes - Subscriptions | CUT SAICH |  |

Addendum

In addition, several other activities were suggested. These are listed below as follows:

- UNESCO ROSA to write to participating countries and to make them aware of the need support and contributions in whatever form.

- ROSA to research and provide feedback to workshop delegates on the procedures that can be followed towards the establishment of a UNESCO Centre Category 2 before the next meeting scheduled for April in Lesotho.

- To conduct a stakeholder mapping exercise, to find out the various roles the stakeholders play and the possible areas in which they could be of assistance

- To build on achievements mad so far and to develop proposals as multinational IARs for SAICH participating countries.

- To partner with the private sector on specific projects.

For the realization of some of the activities listed above the meeting came up with some possible resource mobilization initiatives, including:

- Apply to UNESCO Participation Program available online annually http://www.unesco.org/pp

- Submit IARS regularly

- Sell publications online

- Publications on inventoried ICH element

- Country reports on the implementation of 2003 Convention

- Engage with universities through research

- Source government funding through member states contribution/donations

- Seek direct one-off contributions

- Lobby focal establishment of SADC Desk on Culture

- Domesticate the 2003 Convention

- Strengthen/train more ICH facilitators

- Lobby for ICH policy and legislation

Closure

The SAICH Platform Coordination Workshop in Lilongwe was officially closed at the end of day 2 by Dr. P. Kaliba, the Deputy Director for Museums and Monuments in Malawi. In his brief closing remarks, Dr, Kaliba thanked country representatives for their contributions towards the activities of the SAICH Platform and pledged Malawi’s continued support in the future.

ANNEXURES

Annex 1:

MAJOR ACTIVITIES AND DELIVERABLES OF THE NEW PHASE OF THE PROJECT

The purpose of the Malawi workshop was to formally kick-start activities of the final phase of this capacity building project on ICH safeguarding in seven countries in Southern Africa, which is supported by the Flanders Government under the auspices of the UNESCO Regional Office for Southern Africa (ROSA). This sub-regional cooperation project is coordinated by the SAICH Platform, which was created for that purpose in 2015 and is hosted by Chinhoyi University of Technology (CUT) in Zimbabwe.

The new project phase will be very intensive and it will only run until June 2019. During this short period, three workshops will be held, starting with the workshop in Malawi in February to plan these activities in detail, followed by a SAFE training workshop in Lesotho in April, and winding up with a review workshop in June most probably on a virtual platform.

Thus the planning workshop in Malawi will ensure that the final stage of the chain of phases of ICH safeguarding and capacity building in Southern Africa will guide and assist the structures that have already been established in previous phases of this project since its inception in 2010, i.e. national ICH committees, ICH database, the Platform and the proposed network of academic institutions in their strategic planning towards self-sustainable functioning.

The four (4) major activities and nine (9) deliverables of this new phase of the project, which guided the Lilongwe workshop, are as follows:

- Upgrading and constant maintenance of the SAICH website and database to build a strong tech hub that will provide a vibrant and interactive platform for ICH information dissemination, sharing and dialoguing.                                                                  DELIVERABLES:

- #1. Workshop 1, January, Malawi  Narrative and Financial Report by 28 February [CUT]

- #2.  Enhanced SAICH Platform website and ICH database – setting up, training, maintenance, access and use [CUT]

- Analysing the context for and challenges facing the National Intangible Cultural Heritage Committees of the participating countries and developing strategies for revitalizing them.

DELIVERABLE:

- #3: Guidelines on structure and TORs of NICH Committees or equivalent national agencies [FPPs]

- Awareness raising and domesticating the 2003 ICH Convention by translating it into selected languages that are widely spoken in the seven participating countries.

DELIVERABLES:

- #4: Workshop 2, April, Lesotho  Narrative & Financial Report by 15 May [CUT]

- #5: Translated versions of the Basic Texts of the 2003 ICH Convention in at least one language per country [FPPs]

- #6:  Awareness-raising materials produced and disseminated in the same language, both in print and in audio-visual formats [FPPs]

- Training (ToT) in elaboration of safeguarding plans (SAFE) while also addressing issues of gender equality and ethics; and

DELIVERABLES:

- #7: Workshop 2, April, Lesotho  Narrative and Financial Report by 15 May [CUT]

- #8: Research publications on ICH safeguarding and ethics, gender equality and youth  manuscript/manual [CUT & SAICHA-Net

- Workshop 9, June, Virtual Platform  Final Narrative Report and certified overall Financial Report by 30 June [CUT]

Annex 2:  LILONGWE WORKSHOP PROGRAM

DAY 1: SUNDAY 10TH FEBRUARY, 2019

All day:		Arrival of delegates

DAY 2: MONDAY 11TH FEBRUARY, 2019

Session 1: Chair - Mr. C.J. Magomelo (Program Officer for Culture, Malawi National Commission for UNESCO)

08:30 – 10:00 am:	Official Opening

Welcome remarks by Director of Ceremonies (Mr. C.J. Magomelo)

Remarks by the Acting Executive Secretary, Malawi National Commission for UNESCO (Mr.  D. Mulera)

Remarks by the SAICH Platform Coordinator at Chinhoyi University Technology (Prof. H. Chimhundu)

Remarks by Representative of the UNESCO Regional Office for Southern Africa (Mr. R. Bunhiko)

Remarks by the Principal Secretary for Civic Education, Culture and Community Service (Mrs. I. Luhanga)

Address by the Guest of Honour, the Minister of Civic Education, Culture and Community Services, Honourable Overton Chimlirenji, MP

10:00 – 10:30am:	Health Break and Group Photograph

Session 2: Chair - Mr. L. Mazibuko (Focal Point Person – Malawi)

10:30 – 11:00am:	Review and adoption of the workshop program

General review of activities carried out during 2016-17 vis-à-vis expected results and outputs of the new project phase (Mr. R. Bunhiko)

11:00 – 12:00noon	Strengthening the existing program and reinforcing the SAICH Cooperation Platform (All)

12:00 – 12:30noon	Standardising the structure, guidelines and operational procedure of the National ICH Committees (All)

12:30 – 1:30pm	Lunch Break

Session 3: Chair -  Ms T.C. Mapena (Focal Point Person – Lesotho)

1:30 – 2:00pm 	Further development of and support for the personnel and structures for implementing the ICH Convention in the communities and at the national level (Mr. E. Kautondokwa)

2:00 – 3:00pm	Domesticating the 2003 ICH Convention by translating it into selected languages that are widely spoken in the seven participating countries (Prof. J. Mapara)

DAY 3: TUESDAY 12TH FEBRUARY, 2019

Session 4: Chair – Ms. T. Nkambule

8:30 – 9:00am	Enhanced Platform website and ICH database, setting up training, maintenance, access and use – Mr. E. Ncube

9:00 – 9:30pm	Production and disseminating publicity materials both print and audiovisual – video show

Session 5: Chair – Ms. N. Kubanji

9:30 - 10:00am	Advice on compiling nomination files and International Assistance Requests – Mr. M. Munyima

Multinational nomination of the mbira/sansi for inscription on the Representative List – Malawi and Zimbabwe

10:00 – 10:30am	Health Break

10:30 – 11:30pm	Special reports:

Workshop on Policy Development on ICH in Southern Africa, October 2016 – Zambia

SAICHA Net – Prof. J. Mapara/C. Magomelo

Session 6: Chair – Mr. Munyima

11:30 – 1:00pm	Looking at the Future – Action Plans and Sustainability

Summary report on Workshop proceedings by Rapporteurs

Closing Remarks by Director of Museums and Monuments – Dr. P. Kaliba

Lunch Break and End of Program

# Annex 3: LIST OF WORKSHOP PARTICIPANTS

| No. | Name and Position | Contact Address | Contact Tel. No./Email |
| --- | --- | --- | --- |
| 1. | Mrs Ivy Luhanga Principal Secretary (Guest of Honour) | Ministry of Civic Education, Culture and Community Development, P/Bag 384, Lilongwe | ivyluhanga@yahoo.com |
| 2. | Herbert Chimhundu SAICH Platform Coordinator | Chinhoyi University of Technology, P/Bag 7724, Chinhoyi, Zimbabwe | +263 719080686 h.v.chimhundu@gmail.com |
| 3. | Erastus Kautondokwa | P O Box 99302, Windohoek, Namibia P/Bag 13186, Windhoek, Namibia | +264 61 2934236 erastsk@yahoo.com |
| 4. | Freda M Tawana Namibia ICH Secretariat | Ministry of Education, Arts & Culture, Luther Street, Government Office Park, P/Bag 13186, Windhoek, Namibia | +264 61 2933545 +264 61 2933901 fredatawana@@gmail.com |
| 5. | Temahlubi Dudu Nkambule | Eswatini National Trust Commission, Box 100, Lobamba, Eswatini, Swaziland | +268 76121311 / ++263 78069550 temahlubin@gmail.com nationalmonuments@snk.org.sz |
| 6. | Biggie Samwanda Director of Arts and Culture | Ministry of Youth, Sports, Arts and Recreation, 20th Floor Mukwati Building, Harare, Zimbabwe | +263 772398171 sabiggie@gmail.com |
| 7. | Lovemore Mazibuko ICH Facilitator | Department of Museums and Monuments, Box 30360, Blantyre 3, Malawi | +265 888551808 lovemoremazibuko@yahoo.com lovemoremazibuko@yahoo.com |
| 8. | David Mulera Acting Deputy Executive Secretary (Education) | Malawi National Commission for UNESCO, Box 30278, Lilongwe 3, Malawi | +265 999939437 dmulera@yahoo.com / dmulera@yahoo.com / mnatcomunesco@mtlonline.mw |
| 9. | Munuka-Yumbwa Munyima | University of Zambia, Institute of Economic and Social Research, Lusaka, Zambia | +260 966393632 munyimam@gmail.com |
| 10. | Tokelo Mapena | Ministry of Tourism, Environment and Culture, Post Office Building, P O Box 52, Lesotho | +266 63078277 tcmapena@gmail.com |
| 11. | Chrissy Chiumia Deputy Director for Museums and Monuments (Conservation) | Malawi National Commission for UNESCO, Box 30278, Lilongwe 3, Malawi | +265 888 344238 cchiumia@gmail.com |
| 12. | Nakiso Kubanji | Ministry of Youth, Empowerment, Sport and Culture Development, Botswana | +267 71619581 / 3935303 nkubanji@gmail.com / nkubanji@gov.bw |
| 13. | Christopher Magomelo Senior Assistant Executive Secretary (Culture) | Malawi National Commission for UNESCO, Box 30278, Lilongwe 3, Malawi | +265 888860537 mnatcomunesco@mtlonline.mw juliomagomelo@gmail.com |
| 14. | Rodney Bunhiko UNESCO Consultant | UNESCO Regional Office for Southern Africa, 8 Kenilworth Road, Newlands, Harare, Zimbabwe | +263 774606937 r.bunhiko@unesco.org |
| 15. | Eugene Ncube CUT SAICH Platform - Consultant | Chinhoyi University Off Harare -Chirundu Road, Private Bag 7724, Chinhoyi, Zimbabwe | +263 779931003 heudgy@gmail.com / ncube.vfx@gmail.com |
| 16. | Jacob Mapara CUT SAICH Platform, Zimbabwe | Chinhoyi University of Technology, Off Harare -Chirundu Highway, Private Bag 7724, Off Harare-Chirundu Highway, Chinhoyi, Zimbabwe | +263 772 387 961 jacob.mapara@gmail.com |
| 17. | Potiphar M. Kaliba Deputy Director for Museums and Monuments (Conservation) | Museums and Monument, P/Bag 384, Lilongwe 3, Malawi | +265 888836336 pmkaliba@yahoo.com |
| 18. | Varaidzo Chinokwetu CUT-SAICH Platform | Chinhoyi University Off Harare -Chirundu Road, Private Bag 7724, Chinhoyi, Zimbabwe | +263 772 387 981 varaidzochm@gmail.com |
| 19. | Charles Mwahara | MBC, Box 162, Lilongwe, Malawi | waharadj@gmail.com |
| 20. | Imaan Mbango | MBC, Box 162, Lilongwe, Malawi | imaansmicembango@gmail.com |
| 21. | Robert Chanunkha | MUST, Box 5196, Limbe, Malawi | 0888307620 rchanunkha@must.ac.mw |
| 22. | Saddock Ng’ambi | Malawi National Commission for UNESCO, Box 30278, Lilongwe 3, Malawi | mnatcomunesco@mtlonline.mw |
| 23. | Estamo Mwagomba | Malawi National Commission for UNESCO, Box 30278, Lilongwe 3, Malawi | mnatcomunesco@mtlonline.mw |
| 24. | Patrick Hara | Malawi National Commission for UNESCO, Box 30278, Lilongwe 3, Malawi | mnatcomunesco@mtlonline.mw |
| 25. | Adamson Zikutherani | Malawi National Commission for UNESCO, Box 30278, Lilongwe 3, Malawi | mnatcomunesco@mtlonline.mw |

# Annex 4:

# CONTRACT GUIDELINES FOR TRANSLATIONS OF THE 2003 ICH CONVENTION

|  | Activity | Implementer | Date |
| --- | --- | --- | --- |
| 1. | Identification of translator(s): at least one language, ideally two languages, per country. | Country Focal Point Person (CFPP) | 28 February 2019 |
| 2. | Submission of name and particulars of identified translator(s) to NICH Committee or responsible Ministry. It is important that the identified translator(s) have a track record in translation, and that their works should be available even online for verification purposes. | CFPP | 8 March 2019 |
| 3. | Contract with translator(s) | CFPP | 8 March 2019 |
| 4. | Draft translation(s) of the document to be presented at the next coordination workshop in Lesotho. NB: Each document has to be signed by the translator as confirmation that the work has been done. | CFPP | April/May 2019 |
| 5. | Standardization of drafts led by SAICH Team at Lesotho workshop (verification procedure, formatting guidelines, etc.). | SAICH Team/CFPP | April/May 2019 |
| 6. | Payment of 50% for translation of the work at the Lesotho Workshop. (Remainder to be paid on submission of final approved version.) | SAICH Team/CFPP | April/May 2019 |
| 7. | Verification of the translation by a reference group of mother-tongue speakers of the target language. | Translator(s)/CFPP | May/June 2019 |
| 8. | Submission of final version of translated version verified by the CFPP/NICH Committee. | CFPP/SAICH Team | 15 June 2019 |
| 9. | Payment of 50% for the translation work and online publication | SAICH Team | 30 June 2019 |

# Annex 5: SAICH PLATFORM DATABASE ACCESS POLICY

- Purpose

This policy provides the principles governing access to ICH data managed by the Southern Africa Intangible Cultural Heritage (SAICH) Platform, a sub-regional ICH network. The policy outlines requirements for granting and revoking access to ICH data on the SAICH Platform.

- Scope and Applicability

- This policy applies to ICH data created or presented by participating countries of SAICH platform. It does not apply to ICH data that is personal property nor to situations in which SAICH is legally compelled to provide access to ICH data in all the respective Member States. This policy is subject to regulations on access to information in general and ICH data in particular in the Member States.

- Audience

The audience for this policy includes all participating countries of the SAICH platform and other interested users, including custodians of culture, academics and cultural practitioners.

- Background

The SAICH is a networking and cooperation platform that operates under the auspices of the United Nations Educational, Scientific and Cultural Organization (UNESCO). SAICH is hosted by Chinhoyi University of Technology (CUT) in Zimbabwe. SAICH has developed a database of ICH from among the seven Member States namely Botswana, Eswatini, Lesotho, Malawi, Namibia, Zambia and Zimbabwe. Providing access to the ICH database is crucial to SAICH’s vision: “To be the regional hub of cooperation, exchanges and support services for implementing activities and programmes in Intangible Cultural Heritage (ICH)”. Access to ICH database shall facilitate participation in protecting, preserving and promoting ICH of the sub-region of Southern Africa.

Before the emergence of SAICH platform, access for cultural practitioners, academics, custodians of culture, and professionals to ICH materials was limited to individual nations and networking, if any, was non-existent. The use of SAICH platform opens to sub-regional networking and cooperation in the implementation of the 2003 Convention for the Safeguarding of Intangible Cultural Heritage.  SAICH members submit ICH products of their respective countries to SAICH platform as required by this policy.  The ICH products may be in the form of texts, audio and visual materials, documentaries, journal articles, and academic books.

Participating countries in SAICH platform shall commit themselves to the creation and submission of ICH database, its access, and expansion of its user base. It is important for SAICH membership to ensure that different generations to come have access to ICH database.

- Policy

Access to ICH database and materials is essential for ICH professionals, practitioners, academics, and others to accomplish SAICH mission of building a vibrant sub-regional platform for the protection, preservation, and promotion of ICH. It is SAICH’s mandate that ICH data of the participating countries regardless of format shall be presented, uploaded, and managed in  the following manner to promote access:

- SAICH shall provide ICH materials or products and services targeted to its membership and other users. These materials and services shall be in electronic formats or hard copy,

- SAICH shall provide general information, programme actions and activities, regulations, and educational materials on ICH.  ICH publications posted on SAICH platform shall adhere to this policy and other applicable SAICH regulations,

- SAICH shall ensure that ICH documents are inventoried, stored, retrieved, and made available to the users,

- SAICH shall institutionalise inclusiveness by providing ICH data accessible to people with disabilities,

- SAICH shall provide access to ICH data in people’s own official language and shall address access barriers the users may face in obtaining ICH data,

- SAICH shall adhere to IP policy and other relevant legal frameworks of the sub-region,

- SAICH shall provide, where available, information on the uses and limits of ICH data loaded on its website. The information provided may describe the purpose of ICH data, its source, documented quality, application, and limitations or cautions in using it,

- SAICH shall issue a disclaimer against using ICH data for other than the purpose intended, to minimize the risk of misinterpretations or abuse,

- SAICH shall provide specifications on the level of preservation needs, promotion requirements, and minimum standard protections for the ICH data before access is granted,

- Accessing ICH data shall require login password to SAICH website free for paid up membership or at a fee for other users,

- SAICH shall ensure that digital payment facility and its procedures are specified,

- SAICH shall put in place procedures for auditing access to ICH data and      revoking access when it is no longer needed.

- Definitions

- Access: Flow of data between a store of data and a user, system, or process. A user, system, or process is considered to have access to data if it has one or more of the following privileges: the ability to read or view the data, update the existing data, create new data, delete data or the ability to make a copy of the data. Access can be provided either on a continual basis or, alternatively, on a one-time or ad-hoc basis. Transferring any data from one party to another in any medium is tantamount to permitting access to those data.

- ICH platform data: Platform data that contain Intangible Cultural Heritage materials, products or information that are promoted under the 2003 UNESCO Convention for Safeguarding Intangible Cultural Heritage.

- Data User: An individual that has been authorized to access data for the performance of his/her job duties.

- Roles and Responsibilities

  - SAICH Platform secretariat is responsible for enforcing this policy.

  - SAICH Platform Member States are responsible for updating or revision of this policy

  - …

- Waiver

There are no generic waivers from this policy. There may be waivers or exemptions for certain specifications in the procedures and standards with concent of Member States.

- Additional Information

For further information about this policy, please contact …

# Annex 6: PROPOSED CONSTITUTION OF SAICHA-NET

Southern Africa Intangible Cultural Heritage Academic Network (SAICHA-Net)

# What is the SAICHA-Network?

The Southern Africa Intangible Cultural Heritage Academic Network (SAICHA-Net) is a network of tertiary academic institutions operating under the auspices of the Southern Africa Intangible Cultural Heritage Platform (SAICH Platform), which is hosted by the Chinhoyi University of Technology (CUT) of Zimbabwe. The SAICH Platform’s ultimate vision is to become a UNESCO Category II Centre on intangible cultural heritage (ICH) for the region.  The setting up of SAICHA-Net was initiated in Harare on 29th September 2018 by participants attending the validation workshop of the report of a survey that was conducted by the SAICH Platform to map the distribution of programmes and courses on ICH and related discipline areas in higher education institutions in Southern Africa. The Network aims at facilitating academic activities that promote exchange in knowledge, experiences and expertise in the study, research, inventorying, promotion and safeguarding of ICH through community engagement.

# Constitution

## 2.1 Members

Members are institutions or organisations within the tertiary education sector that represent a country, a national region or a local community. In principle there can be more than one member from a country. Branches of the same institution in a country shall be considered as one membership. Member countries shall be required to establish national chapters of the network which would comprise all institutions in the member state. After one year of the establishment of the network, no institution that is not part of the national chapter shall be allowed to be a member of the SAICHA-Net. This will ensure networking at country level.

## 2.2 Honorary Members

Honorary Members are individuals who are no longer representing a member institution or organisation but are still willing to cooperate within the SAICHA-Net to fulfil its objectives provided they are still members of the national chapter.

## 2.3 General Assembly

The General Assembly is the convention of the members. All members can be represented by up to three people, are equal and have one vote each. Decisions are taken by the consensus principle. Honorary members do not have the right to vote.

## 2.4 Secretary

The Secretary is one member in charge of the responsibility for organising the General Assembly, which shall be based at Chinhoyi University of Technology

- Implementation

The institutions and bodies of the SAICHA-Net have different tasks and responsibilities, which are described in the following:

## Membership

Membership shall be institutional, except in the case of honorary members. Initially for the first year, institutions or organisations have to officially declare their interest by applying to become a member through the current Secretariat of the SAICH Platform at CUT.  The initial applicants become members by a decision of the General Assembly deliberating, either online or in a meeting. The initial members become the representatives of the National Chapter of the network and are responsible for networking activities and the creation of a national chapter at country level. All subsequent members apply to the national chapter and are formally included in the network at the General Assembly.

## Honorary Membership

Honorary Membership may be offered to any person who has made an outstanding contribution to ICH safeguarding (protection, preservation and promotion) over a number of years and is no longer in employment, or has moved from employment, which entitled them to representative membership provided they remain a member of the national chapter. They may be proposed by any member to the chapter and voted on by members at National Assembly. If the Honorary Member does not attend a national assembly for three years, she or he should be contacted to ascertain their wish to remain as an Honorary Member.

## General Assembly

The calendar of the SAICHA-Net shall be 1st January to 31st December. The General Assembly is the biennial get-together of the members. It can be organised virtually online or physically. Each member and observer is responsible to nominate at least one person to inform the General Assembly about activities in English. It is organised and hosted by the Secretariat. During the General Meeting, the General Assembly is able to adopt decisions. The agenda of the General Assembly should include:

- Approval of membership;

- Scheduling important deadlines (for example, for activity proposals, evaluation of activities, evaluation of the network, registration); and

- Making decisions about further proposals, suggestions or requests of members.

## Secretary

The Secretary’s responsibilities shall be to:

- write and publish a report of the Network;

- host and organise the General Assembly;

- write and publish a report of the General Assembly;

- prepare the evaluation of the Network activities;

- summarize the proposals for future Network activities;

- follow up any actions that have been decided during the last General Assembly and have been published in the report;

- distribute important information to the members and observers (for example, via website, hard-copy or e-mail); and

- take editorial care of the SAICHA- Network page on the SAICH website and database.

# Objectives

The background of all member organisations is different, which means that objectives for activities can be varied. Common objectives of the Network are:

- to support academic mobility and intellectual and intercultural learning;

- to encourage academic participation in safeguarding ICH;

- to foster complementarity between tertiary education institutions and community ICH practitioners;

- to improve ICH safeguarding through informal and non-formal learning;

- to support academic research and other activities related to re-awakening of the African cultural consciousness;

- to foster development of the African epistemology such as Um(b)unthu [unhu/ubuntu/botho…] philosophy;

- to promote regional integration at academic level in ICH activities;

- to participate in Network activities;

- to provide a platform for effective and functioning communication among academic tertiary institutions in the area of culture in the region;

- to share experiences and good practices; and

- to lobby and make ICH policy visible in the member countries.

# Activities

A SAICHA- Network Activity is an activity hosted by one member that engages at least one other partner from the network.

Activities are the best possibility to fulfil the objectives of the Network. There are different kinds of activities, most of them to support development of relevant ICH courses, academic cooperation, intellectual and intercultural learning, and also to share experiences and good practices and others. The most common activities are defined and described below.

## Academic Exchange

A SAICH-Education Network academic exchange is an activity, which brings together groups of academic practitioners from two or more academic institutions whether within one country or not, providing them with an opportunity to discuss and confront various themes, whilst learning about each other’s countries, institutions, academic courses and related cultures.

SAICH-Education Network Activity activities called academic exchanges are mostly financed by funds of any of the participating member countries or the UNESCO Programmes.

## Camp

A camp is a short stay as an international group of students and lecturers in which free time activities, linked to a certain domain of ICH and involving local practicing communities are central.

## Seminar

A seminar is an activity where a group of members come together to share experiences of their work in ICH projects and to develop their skills; for example, in developing new relevant courses, reviewing progress of activities, or to improve or review trusted and continuous partnerships and quality standards for activities.

  - Conference (or Symposium)

A conference (or symposium) is an annual (or biennial) event that is hosted by a participating country at a member academic institution within the host country. Academic papers and posters are presented under a chosen theme every (other) year and proceedings are published and shared with stakeholders.